## ITSD
Section 1: DEPARTMENTAL INFORMATION | [15 empty] | .
Name of Department: | INLAND TRANSPORT SERVICES
DIVISIONS UNDER THE DEPARTMENT | 1
2
3
Section 2: DESCRIPTION OF INITIATIVES PER KRA
S/N | Key Result Areas | Objective | Activity/ Initiative | Leading and Contributing Departments with Total Weight | Assigned weight (For the Department/ Unit/ Outstation | INPUTS | KPI | KPI weight | Graded Weight | Unit of Measurement | Target | START DATE | END DATE | 2ND QUARTER ACHIEVED TARGET | ASSESMENT | SCORE | 3RD QUARTER ACHIEVED TARGET | ASSESMENT | SCORE
Presidential Priorities | 38
GP1 | Policy Development (7%) | Develop and Implement National Policy On Maritime & Blue Economy | Implementation of policy initatives allocated to NSC | All clients facing Department Weight (2%) | 0.5% | Implement National Policy On Maritime & Blue Economy | % implementation of policy initatives allocated to NSC | 0.5% | 760% | % completion | 100 | 2025-04-01 | 31/12/2025 | N/A | N/A | N/A | NA | NA | NA
GP4 | Maritime Infrastructure Development | Complete the construction of critical transport project | Facilitate the Emergence of an Investor for Jos IDP Project | ITSD Zonal Office, PPP Weight (4%) | 2% | Updated OBC to attract investors | % Completion of OBC | 2% | 3040% | % completion | 100 | 2025-04-01 | 30/06/2025 | 100 | 1 | 38 | NA | 1 | 38
TOTAL |  |  |  |  | 2.5% |  |  | 2.5% | 3800% | [6 empty] | 38 |  |  | 38
MDA Operational Priorities | 25%
MP3 | Infrastructure Development | Facilitate the development of additional IDPs (Isiala ngwa, Abia State ) | Bi-annually Meetings with Concessionaires/ Abia State Government for the development of Isiala Ngwa IDP | ITSD -50% PPP- (50%) Weight 3% | 1.5% | Meetings with Concessionaires/ Abia State Government on the development of Isiala NgwaIDP | Number of Meetings with Concessionaires/ Abia State Government for IDP | 0.5% | 25% | number | 2 | 2025-01-01 | 31/12/2025 | 1 | 1 | 25 | 1 | 1 | 25
TOTAL | [7 empty] | 0.5% | 25% | [6 empty] | 25 |  |  | 25
Service Wide Priorities | 37%
C1 | Service Innovation and Improvement | Increase staff productivity through development of Standard Operating Procedures. | Submission of SOPs to HR | SPRD - 0.3% All - 0.08% (each) (1%) | 0.05% | Submit SOPs | Number of weeks taken to submit SOPs | 0.05% | #REF! | Weeks | 24 | 2025-06-01 | 31/12/2025 | 24 | N/A | N/A | NA | NA | NA
|  | Increase staff productivity through development of job descriptions. | Development of staff job descriptions and schedule of duties | HR - 0.8% All - 0.05% (each) (total weight : 1.8%) | 0.05% | Submission of Schedule of Duties to HRMD | Time taken to Submit Schedule of Duties to HRMD | 0.05% | #REF! | Weeks | 4 weeks | 2025-04-01 | 30/04/2025 | Not Submitted as as when due | 0.8 | 3.7 | NA | NA | NA
C2 | Stakeholder Engagement | Promotion of seamless movement of cargo and coordination of modes of transportation | Development of a Memorandum of Understanding (MoU) between NSC and NIWA. |  |  | Issue notice of meetings/engagements with NIWA. | Time taken to issue notice of meeting. (Bi-annual) |  |  | Weeks | 36 | 2025-06-01 | 31/12/2025 | 36 | 1 | 2.3125 | Meeting will hold in Q4 | NA | NA
[6 empty] | Attend Joint Technical Committee meeting and produce report | Number of meetings/engagements on MoU. (Bi-annual) |  |  | Weeks | 36 | 2025-06-01 | 31/12/2025 | 36 | 1 | 2.3125 | NA | NA | NA
[6 empty] | Production of Draft MoU | Time taken to Produce Draft MoU |  |  | Weeks | 12 | 2025-10-02 | 31/12/2025 | N/A | N/A | N/A | seen draft of MOU | 1 | 4.625
C2 | Stakeholder Engagement | Identify and address key operational challenges affecting the Inland Dry Ports (IDPs) in Nigeria. | Bi-annual Monitoring operation activities and data collection at the commissioned Inland Dry Ports (IDPs): Kaduna, Dala and Funtua IDPs. |  |  | Develop template for monitoring. | Time taken to develop the template |  |  | weeks | 12 | 2025-01-01 | 31/03/2025 | N/A | N/A | N/A | NA | NA | NA
[6 empty] | Notify the concessionaires of IDPs (Bi-annual) | Time taken to notify concessionaires |  |  | Week | 1 | 2025-01-01 | 31/12/2025 | 1 | 1 | 2.3125 | NA | NA | NA
[6 empty] | Visit the (3) IDPs operations and produce one report | Time taken to produce report. (Report to be ready, 2 weeks in the new month in the next quarter) |  |  | Weeks | 2 | 1/4/2025 1/10/2025 | 30/4/2025 29/10/2025 | 2 | 1 | 2.3125 | NA | NA | NA
C2 | Stakeholder Engagement | To develop a clear contractual agreement for the establisment of IDPs in Nigeria. | Signing of the Build, Own, Operate and Transfer (BOOT) Agreement. |  |  | Notice of preliminary meeting forwarded to the Federal Ministry of Justice (FMOJ) for the final review. | Time taken to hold Meetings with FMOJ |  |  | weeks | 12 | 2025-04-01 | 30/04/2025 | 12 | 1 | 4.625 | NA | NA | NA
[6 empty] | Escalate draft copy of the reviewed BOOT Agreement to Concessionaires for input. | Time taken to Escalate draft copy of the reviewed BOOT Agreement to Concessionaires |  |  | weeks | 12 | 2025-07-01 | 30/09/2025 | N/A | N/A | N/A | Memo was sent on 7/7/25 | 1 | 2.3125
[6 empty] | Stakeholders engagement to harmonise inputs from the Concessionaires and produce final copy of the reviewed BOOT Agreement | Time Taken to Harmonise inputs from the Concessionaires and produce final copy of the reviewed BOOT Agreement |  |  | weeks | 12 | 2025-07-01 | 30/09/2025 | N/A | N/A | N/A | Response seen 16/09/25 | 1 | 2.3125
[6 empty] | Convene a Stakeholders meeting for signing of the BOOT Agreement. | Time taken to convene Stakeholders meeting for signing of the BOOT Agreement |  |  | weeks | 12 | 2025-10-02 | 31/12/2025 | N/A | N/A | N/A | NA | NA | NA
C2 | Stakeholder Engagement | Sensitization Programme for Government Agencies and Users/Providers of Inland Tranport Services | Inter Agency Sensitization Programme | 0.125% | 0.125% | Develop and Submit Proposals for Two (2) Enlightement Programmes | Time taken to Develop and Submit Proposals for Enlightement Programmes | 0.125% | #REF! | weeks | 2 | 2025-06-01 | 31/12/2025 | 1 | 1 | 2.3125 | proposal sighted | 1 | 4.625
|  |  |  | 0.125% | 0.125% | Submit report of sensitization Program after programme (Bi annual) | number of weeks taken to submit report of sensitization Program after programme | 0.125% | #REF! | weeks | 2 | 2025-06-01 | 31/12/2025 | Approved but no payment | 0.75 | 1.7344 | NA | NA | NA
C5 | Support for Service Delivery | Effective Collection and Collation of relevant Trade and Transport Data | Submission of Quarterly Progress Report |  |  | Call Circular for submission of Progress Report to Departments/ Units and Outstations | Time taken to receive call Circular from SPRD |  |  | weeks | 1 week | 17/03/2025 16/06/2025 15/09/2025 15/12/2025 | 21/03/2025 20/06/2025 19/21/2025 19/12/2025 | 1 week | 1 | 2.3125 |  | 1 | 2.3125
[6 empty] | Submission of Departmental/Unit/ Outstation Progress Report to SPRD | Time taken to submit Progress Report to SPRD |  |  | days | 14 days | 1/4/2025 1/07/2025 1/10/2025 1/01/2026 | 11/4/2025 11/07/2025 10/10/2025 9/01/2026 | 14 days | 1 | 2.3125 | Report sighted | 1 | 2.3125
C5 | Support for Service Delivery | Effective Communication and Monitoring of actvities of Departments, Units and Outstations. | Departmental, Unit and Outstation Meetings |  |  | Issue Notices of meetings. | Time taken to issue Notice of meetings |  |  | days | 7 days before meetings. | 2025-01-01 | 31/12/2025 | Notice not issued as at when due | 0.14286 | 0.33036 | Notice of meeting seen | 1 | 2.3125
[6 empty] | Hold Departmental, Unit and Outstation meetings | Number of Meetings Held (Attendance and minutes of the meetings) |  |  | no of weeks | 1 every quarter. | 2025-02-01 | 31/12/2025 | 1 every quarter. | 1 | 2.3125 | Attendance and Report seen | 1 | 2.3125
C5 | Support for Service Delivery | To Ensure Availability of Working Materials and Quality Delivery of Works & Services. | Procurement Needs Assessment |  |  | Call Circular for submission of Procurement needs to Departments/ Units and Outstations | Time taken to receive Call Circular from Procurement Needs |  |  | week | 1 week | 2025-03-11 | 2025-07-11 | N/A | N/A | N/A | NA | NA | NA
[6 empty] | Submit Departmental/Unit/ Outstation Procurement needs | Time taken to submit Procurement needs to Procurement Unit |  |  | weeks | 6 weeks | 2025-11-10 | 2025-12-31 | N/A | N/A | N/A | NA | NA | NA
C5 | Support for Service Delivery | Improve and sustain Human Capital Development through Timely Submission of Training Needs | Staff Training Needs |  |  | Call Circular on staff training needs for year 2026 | Time taken to receive Call Circular from HRMD |  |  | weeks | 4 weeks | 2025-01-10 | 31/10/2025 | N/A | N/A | N/A |  | 1 | 2.3125
[6 empty] | Prepare and Submit Staff Training needs for year 2026 | Time taken to Submit Training needs for year 2026 to HRMD |  |  | weeks | 12 weeks | 2025-01-10 | 31/12/2025 | N/A | N/A | N/A | Training needs submitted | 1 | 2.3125
C4 | Capacity Building & Talent Management | Ensure all Nominated Staff attend Training Programmes and Imbibe a Train-the-Trainers Philosophy of Staff Cascading Knowledge Acquired | Staff Training |  |  | Staff nominated to submit copy of Training Report and Certificate | Time taken to Submit Certificate(s) and Report(s) to HRMD |  |  | Days | 14 days | 2025-01-01 | 31/12/2025 | No Evidence | 0 | 0 | attended training o the 15/08/25 | 1 | 2.3125
[6 empty] | Conduct Knowledge Sharing | Time taken to Conduct Knowledge Sharing |  |  | Days | 21 days | 2025-01-01 | 31/12/2025 | No Evidence | 0 | 0 | Knowledge sharing conducted on 25/08/2025 | 1 | 2.3125
C2 | Engagements with Stakeholders | Improve perfomance through innovation | Improve Operational efficiency |  |  | New initiative(s)developed in the Departments/ Units and Outstations. | number of new initiatives developed. |  |  | number of Initiatives | 1 | 2025-01-01 | 31/12/2025 | N/A | N/A | N/A | seen | 1 | 4.625
[17 empty] | 28.8897 |  | 37
[14 empty] | 2ND QUARTER OVERALL SCORE |  | 91.8897 |  | Q3 TOTAL SCORE | 100